## Brief Conenct UAT- Test Summary
Sprint | ID | Work Item Type | Title | Status | UAT completed
Sprint 1 | 53803 | User Story | Combobox search for large datasets | PASS | 22/07/2025
Sprint 1 | 57425 | User Story | Collapse/hide the correspondence file information on subsequent screens | Only System Testing(Config) - No UAT
Sprint 1 | 56710 | User Story | Show full column title in popover on column header hover - Dashboard | PASS | 22/07/2025
Sprint 1 | 57014 | User Story | Update dropdown values | PASS | 22/07/2025
Sprint 1 | 57295 | User Story | Make all comments optional | PASS | 24/07/2025
Sprint 1 | 57296 | User Story | Open documents in a new browser tab | PASS | 24/07/2025
Sprint 1 | 57632 | User Story | NEW - Reword Descriptions for Document Headings | PASS | 24/07/2025
Sprint 1 | 58522 | User Story | NEW - Update permissions for all record types | Pending
Sprint 1 | 58546 | User Story | NEW - Create the CC Role | PASS | 24/07/2025
Sprint 2 | 56678 | User Story | Add live preview of recommendations | PASS | 29/07/2025
Sprint 2 | 56690 | User Story | Add Primary Correspondence to PDF Pack | PASS | 29/07/2025
Sprint 2 | 56701 | User Story | Allow adding supporting documentation to closed records | PASS | 31/07/2025
Sprint 2 | 56709 | User Story | Add option to disable SP uploads - env variable | PASS | 31/07/2025
Sprint 2 | 56980 | User Story | Restricting Multiple Document Upload for PPQ and Parliamentary Items | PASS | 2025-05-08
Sprint 2 | 57006 | User Story | Add a possibility to disable signatures on record type level | PASS | 2025-05-08
Sprint 2 | 57015 | User Story | Allow to upload documents by dragging | PASS | 2025-07-08
Sprint 2 | 57030 | User Story | Role Reassignment permissions | PASS | 2025-07-08
Sprint 2 | 57277 | User Story | Update Information Request Record Type | PASS | 2025-07-08
Sprint 2 | 57278 | User Story | Update Speech Request Record Type | PASS | 2025-12-08
Sprint 2 | 57279 | User Story | Update Video Request Record Type | PASS | 2025-12-08
Sprint 2 | 57282 | User Story | Update Briefing for Decision Record Type | PASS | 2025-12-08
Sprint 2 | 57283 | User Story | Update Briefing for Noting Record Type | PASS | 14/08/2025
Sprint 2 | 57284 | User Story | Update Briefing for Event Record Type | PASS | 14/08/2025
Sprint 2 | 57285 | User Story | Update Briefing for Meeting Record Type | PASS | 14/08/2025
Sprint 2 | 59138 | User Story | NEW - Replace VATL with 'The Academy' | PASS | 26/08/2025
Sprint 3 | 56996 | User Story | Ability to specify task due dates | PASS | 26/08/2025
Sprint 3 | 57268 | User Story | Add current role assigned to the dashboard | PASS | 28/08/2025
Sprint 3 | 57422 | User Story | Filter Activity Panel entries | PASS | 2025-02-09
Sprint 3 | 57085 | User Story | Enhance clone record functionality | PASS | 2025-02-09
Sprint 3 | 56704 | User Story | Remove recording decision and hide recommendations for some record types | PASS | 2025-03-09
Sprint 3 | 57006 | User Story | Add a possibility to disable signatures on record type level | PASS | 2025-03-09
Sprint 3 | 57024 | User Story | Add fields to Correspondence (COR) header and PDF pack | FAIL | 2025-04-09
Sprint 4 | 59506 | User Story | NEW - Display only four sensitivity labels and enforce MaPS-specific access rules | PASS | 2025-07-10
Sprint 4 | 57421 | User Story | Automatic cover page signature block | FAIL | 2025-07-10
Sprint 4 | 57401 | User Story | Add option to upload signed doc during decision-making process | PASS | 2025-09-10
Sprint 4 | 57388 | User Story | Enhance Signature functionality | PASS | 2025-09-10
Sprint 4 | 56703 | User Story | Add a possibility to save views (import DGS feature) | PASS | 2025-09-10
Sprint 4 | 57772 | User Story | NEW - Delegate Workflow Action | Pending
Sprint 4 | 56693 | User Story | Improve how historic actions/tasks completed are recorded in timeline and activity log (PastTenseVerb) | PASS | 14/10/2025
Sprint 4 | 57269 | User Story | Change Information Security Classification impact on permissions | PASS | 14/10/2025
Sprint 5 | 55610 | User Story | Ability to configure which users can create certain record types | Only System Testing(Config)
Sprint 5 | 55648 | User Story | Configurable Document Metadata | PASS | 15/10/2025
Sprint 5 | 57423 | User Story | Enhance Field Placement and Section Grouping in Record Wizards and Metadata Forms | PASS | 15/10/2025
Sprint 5 | 57085 | User Story | Enhance clone record functionality | PASS | 15/10/2025
Sprint 5 | 57090 | User Story | Auto-assign CPU Team as initiator | Pending
Sprint 5 | 57124 | User Story | Change the default notification settings for all users | Pending
Sprint 5 | 57272 | User Story | Update Correspondence Record Type | Pending
Sprint 5 | 57336 | User Story | Update Cabinet Submission Record Type | Pending
Sprint 5 | 57351 | User Story | Enhance 'Notify others about the record' functionality | Pending
Sprint 5 | 57419 | User Story | Cabinet Submission Workflow Changes | Pending
Sprint 5 | 58702 | User Story | Parliamentary Items (ADJ, CQU, QWN) Workflow Changes | Pending
Sprint 5 | 58703 | User Story | PPQ Workflow Changes | Pending
Sprint 5 | 58705 | User Story | CabBRI Workflow Changes | Pending
Sprint 5 | 58795 | User Story | NEW - Add Supplementary Area Detail Entry Tab to Brief Connect | Pending
Sprint 5 | 60116 | User Story | Custom email notifications | Pending
Sprint 5 | 61342 | User Story | NEW - Change structure of PDF Pack | Pending

## UAT Reporting
Sprint | ID | Work Item Type | Title | Status
Sprint 5 | 56424 | User Story | Create dimension tables for record types. | Pending
Sprint 5 | 56186 | User Story | Add record count to all tabular report tables and template | Pending
Sprint 5 | 56176 | User Story | Add date slicers to CPU and MPS blank templates, and to all MPS reports | Pending
Sprint 5 | 56185 | User Story | Add a 'restricted' column and filter to MPS reports | Pending
Sprint 5 | 56170 | User Story | Match the 'workflow stage' column to the ABC 'action' | Pending
Sprint 5 | 59081 | User Story | Add links to records in BriefConnect to all tabular-style reports. | Pending
Sprint 5 | 56180 | User Story | Paginated report - Template | Pending
Sprint 5 | 56177 | User Story | Paginated report - CPU DE Cabinet Submissions | Pending
Sprint 5 | 56179 | User Story | Paginated report - CPU Coordination Comments | Pending
Sprint 5 | 56178 | User Story | Paginated report - CPU Non-DE Cabinet Submissions | Pending
Sprint 5 | 56175 | User Story | Reorder filters (slicers) on all tabular reports | Pending