## Slide 1: Brief Connect
BC User Acceptance Testing – Sprint Cycle 1 to 5 & End to End Regression Testing
December 2024

## Slide 2: About this document
This Test Plan defines the approach to UAT prior to deployment into production to ensure the solution is fit for purpose, meets business requirements, and is of high quality. The strategy outlined in this document covers the scope, approach, responsibilities, and success criteria for testing to support a reliable and successful production release.
Requirements Scope: Brief Connect requirements
Testing Scope: The scope and types of testing that will be undertaken at UAT
Environments: UAT
Roles and Responsibilities: UAT users with specific roles
Test Tooling: Azure DevOps

## Slide 3: BC Sprint Cycle 1 - Completed
The following user stories are included in BC Sprint Cycle 1:
    Combobox search for large datasets
    Collapse/hide the correspondence file information on subsequent screens
    Show full column title in popover on column header hover - Dashboard
    Update dropdown values
    Make all comments optional
    Open documents in a new browser tab
    NEW - Reword Descriptions for Document Headings
    NEW - Create the CC Role
    Outcome: We have completed the UAT for Sprint 1, analysed the results, raised defects where required.

## Slide 4: User Acceptance Testing Execution Result – Sprint Cycle 1
Sprint | ID | Title | Status | UAT completed
Sprint 1 | 53803 | Combobox search for large datasets | PASS | 22/07/2025
Sprint 1 | 57425 | Collapse/hide the correspondence file information on subsequent screens | Only System Testing(Config) | N/A
Sprint 1 | 56710 | Show full column title in popover on column header hover - Dashboard | PASS | 22/07/2025
Sprint 1 | 57014 | Update dropdown values | PASS | 22/07/2025
Sprint 1 | 57295 | Make all comments optional | PASS | 24/07/2025
Sprint 1 | 57296 | Open documents in a new browser tab | PASS | 24/07/2025
Sprint 1 | 57632 | NEW - Reword Descriptions for Document Headings | PASS | 24/07/2025
Sprint 1 | 58522 | NEW - Update permissions for all record types | Pending | 
Sprint 1 | 58546 | NEW - Create the CC Role | PASS | 24/07/2025

## Slide 5: BC Sprint Cycle 2 - Completed
The following user stories are included in BC Sprint Cycle 2:
Add live preview of recommendations
Add Primary Correspondence to PDF Pack
Allow adding supporting documentation to closed records
Add option to disable SP uploads - env variable
Restricting Multiple Document Upload for PPQ and Parliamentary Items
Add a possibility to disable signatures on record type level
Allow to upload documents by dragging
Role Reassignment permissions
Update Information Request Record Type

## Slide 6: BC Sprint Cycle 2 - Completed
Update Speech Request Record Type
Update Video Request Record Type
Update Briefing for Decision Record Type
Update Briefing for Noting Record Type
Update Briefing for Event Record Type
Update Briefing for Meeting Record Type
NEW - Replace VATL with 'The Academy’
Outcome: We have completed the UAT for Sprint 2, analysed the results, raised defects where required and some change request for metadata fields

## Slide 7: User Acceptance Testing Execution Result – Sprint Cycle 2
Sprint | ID | Title | Status | UAT completed
Sprint 2 | 56678 | Add live preview of recommendations | PASS | 29/07/2025
Sprint 2 | 56690 | Add Primary Correspondence to PDF Pack | PASS | 29/07/2025
Sprint 2 | 56701 | Allow adding supporting documentation to closed records | PASS | 31/07/2025
Sprint 2 | 56709 | Add option to disable SP uploads - env variable | PASS | 31/07/2025
Sprint 2 | 56980 | Restricting Multiple Document Upload for PPQ and Parliamentary Items | PASS | 5/8/2025
Sprint 2 | 57006 | Add a possibility to disable signatures on record type level | PASS | 5/8/2025
Sprint 2 | 57015 | Allow to upload documents by dragging | PASS | 7/8/2025
Sprint 2 | 57030 | Role Reassignment permissions | PASS | 7/8/2025
Sprint 2 | 57277 | Update Information Request Record Type | PASS | 7/8/2025
Sprint 2 | 57278 | Update Speech Request Record Type | PASS | 12/8/2025
Sprint 2 | 57279 | Update Video Request Record Type | PASS | 12/8/2025
Sprint 2 | 57282 | Update Briefing for Decision Record Type | PASS | 12/8/2025
Sprint 2 | 57283 | Update Briefing for Noting Record Type | PASS | 14/08/2025
Sprint 2 | 57284 | Update Briefing for Event Record Type | PASS | 14/08/2025
Sprint 2 | 57285 | Update Briefing for Meeting Record Type | PASS | 14/08/2025
Sprint 2 | 59138 | NEW - Replace VATL with 'The Academy' | PASS | 26/08/2025

## Slide 8: BC Sprint Cycle 3 - Completed
The following user stories are included in BC Sprint Cycle 3:
Ability to specify task due dates
Add current role assigned to the dashboard
Filter Activity Panel entries
Enhance clone record functionality
Remove recording decision and hide recommendations for some record types
Add a possibility to disable signatures on record type level
Add fields to Correspondence (COR) header and PDF pack
Outcome: We have completed the UAT for Sprint 3, analysed the results, raised defects where required and change request for workflow, notifications and supplementary area

## Slide 9: User Acceptance Testing Execution Result – Sprint Cycle 3
Sprint | ID | Title | Status | UAT completed
Sprint 3 | 56996 | Ability to specify task due dates | PASS | 26/08/2025
Sprint 3 | 57268 | Add current role assigned to the dashboard | PASS | 28/08/2025
Sprint 3 | 57422 | Filter Activity Panel entries | PASS | 2/9/2025
Sprint 3 | 57085 | Enhance clone record functionality | PASS | 2/9/2025
Sprint 3 | 56704 | Remove recording decision and hide recommendations for some record types | PASS | 3/9/2025
Sprint 3 | 57006 | Add a possibility to disable signatures on record type level | PASS | 3/9/2025
Sprint 3 | 57024 | Add fields to Correspondence (COR) header and PDF pack | FAIL | 4/9/2025

## Slide 10: BC Sprint Cycle 4 - Completed
The following user stories are included in BC Sprint Cycle 4:
NEW - Display only four sensitivity labels and enforce MaPS-specific access rules
Automatic cover page signature block
Add option to upload signed doc during decision-making process
Enhance Signature functionality
Add a possibility to save views (import DGS feature)
NEW - Delegate Workflow Action
Improve how historic actions/tasks completed are recorded in timeline and activity log
Change Information Security Classification impact on permissions
Outcome: We have completed the UAT for Sprint 4, analysed the results, raised defects where required and change request for Cabinet draft stage, PPQ bulk download, PPQ Bulk update.

## Slide 11: User Acceptance Testing Execution Result – Sprint Cycle 4
Sprint | ID | Title | Status | UAT completed
Sprint 4 | 59506 | NEW - Display only four sensitivity labels and enforce MaPS-specific access rules | PASS | 7/10/2025
Sprint 4 | 57421 | Automatic cover page signature block | FAIL | 7/10/2025
Sprint 4 | 57401 | Add option to upload signed doc during decision-making process | PASS | 9/10/2025
Sprint 4 | 57388 | Enhance Signature functionality | PASS | 9/10/2025
Sprint 4 | 56703 | Add a possibility to save views (import DGS feature) | PASS | 9/10/2025
Sprint 4 | 57772 | NEW - Delegate Workflow Action | Pending | 
Sprint 4 | 56693 | Improve how historic actions/tasks completed are recorded in timeline and activity log (PastTenseVerb) | PASS | 14/10/2025
Sprint 4 | 57269 | Change Information Security Classification impact on permissions | PASS | 14/10/2025

## Slide 12: BC Sprint Cycle 5 - Completed
The following user stories are included in BC Sprint Cycle 5:
Ability to configure which users can create certain record types
Configurable Document Metadata
Enhance Field Placement and Section Grouping in Record Wizards and Metadata Forms
Enhance clone record functionality
Outcome: We have completed the UAT for Sprint 5, analysed the results, raised defects where required and change request for Power Bi reporting, document signature management

## Slide 13: User Acceptance Testing Execution Result – Sprint Cycle 5
Sprint | ID | Title | Status | UAT completed
Sprint 5 | 55610 | Ability to configure which users can create certain record types | Only System Testing(Config) | N/A
Sprint 5 | 55648 | Configurable Document Metadata | PASS | 15/10/2025
Sprint 5 | 57423 | Enhance Field Placement and Section Grouping in Record Wizards and Metadata Forms | PASS | 15/10/2025
Sprint 5 | 57085 | Enhance clone record functionality | PASS | 15/10/2025

## Slide 14: BC E2E UAT– Planned(Week 08/12/2025)
The following user stories are included in BC E2E UAT:
E2E testing for CAB SUB Record Type (Planned -08/12/2025 – Monday)
E2E testing for Correspondence Record Type (Planned – 09/12/2025 – Tuesday)
E2E testing for Briefing for Decision Record Type (Planned – 11/12/2025 – Tuesday)
E2E testing for Briefing for Noting Record Type (Planned – 11/12/2025 – Tuesday)
E2E testing for CAB CRD Record Type(Planned – 12/12/2025 – Tuesday)
E2E testing for CAB BRI Record Type(Planned – 12/12/2025 – Tuesday)

## Slide 15: BC E2E UAT– Planned(17/12/2025)
The following user stories are included in BC E2E UAT:
E2E testing for Briefing for Event Record Type (Planned – 17/12/2025 –Wednesday)
E2E testing for Briefing for Meeting Record Type (Planned – 17/12/2025 –Wednesday)

## Slide 16: BC E2E UAT– Planned(Week 12/01/2026)
The following user stories are included in BC E2E UAT:
E2E testing for Speech Request Record Type (Planned – 13/01/2026- Tuesday)
E2E testing for Video Request Record Type (Planned – 13/01/2026 -Tuesday)
E2E testing for Information Request Record Type((Planned – 14/01/2026 - Wednesday)
E2E testing for PPQ Record Type (Planned -15/01/2026 - Thursday)
Power BI reporting MPS & CPU (Planned - 16/01/2026 - Friday)

## Slide 17: BC E2E UAT– Planned(Week 19/01/2026)
The following user stories are included in BC E2E UAT:
E2E testing for ADJ Record Type (Planned - 20/01/2026- Tuesday)
E2E testing for QwN Record Type (Planned - 20/01/2026 - Tuesday)
E2E testing for QoN Record Type (Planned - 20/01/2026 - Tuesday)
E2E testing for CQU Record Type (Planned - 20/01/2026- Tuesday)